THE PUBLISHERS HOUSE

Website Implementation Plan

Target Deadline: October 9, 2026  |  thepublishershouse.org

[IMPORTANT] Confirmed Stack: Next.js 14 (App Router) · Strapi CMS · Paystack / Flutterwave · Cloudflare (domain already live)

## What This Plan Is Built From

Life.Church /who-we-are/ — "Who We Are / What to Expect / Our Beliefs" three-section structure with leadership cards and bold statement sections.

FaithAndWork.com — Premium editorial feel, full-bleed hero, tight type-led layout, program cards, and a prominent "Give" CTA in the nav.

GospelInLife.com/donate/ — Clean multi-category giving page, preset amounts, one-time vs. recurring toggle, friction-free form.

## Expanded Sitemap (All Pages)

| # | Page | URL | Priority |
| --- | --- | --- | --- |
| 1 | Homepage | / | Critical |
| 2 | About Us | /about | Critical |
| 3 | Resources | /resources | Critical |
| 4 | Articles | /articles | High |
| 5 | Our Programs | /programs | High |
| 6 | Giving | /giving | Critical |
| 7 | Events | /events | High |
| 8 | Contact Us | /contact | Medium |
| 9 | Watch Live | /live | Future |

## Page-by-Page Design Spec

### 1. Homepage /

Inspired by FaithAndWork.com's editorial hero + program cards

Full-bleed Hero — Cinematic church image or video loop, large headline, service times overlay, 'Plan Your Visit' CTA

Latest Sermon Card — Featured most-recent sermon with thumbnail, title, speaker, play button

Upcoming Events Strip — Horizontal scroll of 3–4 upcoming event cards (from CMS)

About the Church Teaser — Short mission statement with 'Learn More' → /about

Programs Spotlight — 3-column card grid: Festival of Light, The Forge, Merismos, AAC, etc.

Give CTA Banner — Full-width: 'Partner with us' + giving category buttons

Latest Articles Row — 3 recent blog post cards

Footer — Logo, nav links, social handles, address, service times

### 2. About Us /about

Modelled on Life.Church's 3-section structure

Section A — Who We Are: Full-bleed hero + 2-column split (text left, pastor photo right)

Section B — What to Expect: Icon + text cards (Worship, Community, Word, Prayer, Children)

Section C — Our Beliefs: Accordion/cards per doctrinal statement with Scripture refs

Section D — Leadership: Portrait cards grid (name, title, bio on hover/click)

### 3. Resources /resources

Hub page with tab navigation

Sermons tab (default) — Paginated grid; filter by Speaker, Series, Topic, Date; audio player + video + PDF guide

Teachings tab — Structured teaching series (Bible studies, special sessions), sub-categorised

Search bar spanning both tabs

### 4. Articles /articles

3-column grid layout

Category filter: Faith, Devotionals, Family, Leadership, Announcements

Search input

Each card: cover image, title, author, date, category, excerpt

Individual article pages with social share buttons

### 5. Our Programs /programs

Hero — 'Where Community Meets Purpose' headline

Program cards: Festival of Light, The Forge, Merismos, AAC (+ more to be confirmed)

Each program: hero image, name, tagline, 2–3 line description, 'Learn More' button

Each program has its own subpage: /programs/festival-of-light, etc.

Program detail: banner, description, schedule/dates, gallery, registration CTA

### 6. Giving /giving

Inspired by GospelInLife.com/donate/ — clean, purposeful, friction-free

Hero — 'Your generosity builds the Kingdom'

4 Giving Categories: Tithe, Offering, Special Projects, Thanksgiving

Give Now Form: preset amounts (N5,000 / N10,000 / N25,000 / Custom), one-time vs. recurring toggle, Name + Email, Paystack CTA

Why Give? — short theology of giving section

Bank Transfer Option — church account details for manual transfer

Confirmation emails automated on successful payment

### 7. Events /events

Calendar view toggle + card list view

Upcoming events: banner, title, date/time, venue, description, registration link

Past events archive

Filter by: Conference, Special Service, Programs, Community

### 8. Contact Us /contact

Google Maps embed (church location)

Contact form (Name, Email, Subject, Message)

Phone numbers + WhatsApp link

Service times summary

Social media handle links

## Step-by-Step Build Timeline (To October 9)

| Phase | Period | Focus |
| --- | --- | --- |
| Phase 1 — Foundation Sprint | Now → Aug 3 | Assets delivery, CMS setup, design tokens, Next.js init |
| Phase 2 — UI Design | Aug 4 → Aug 17 | Brother AY: hi-fi Figma mockups (all pages, desktop + mobile) |
| Phase 3 — Core Frontend Build | Aug 18 → Sep 7 | Micha: all pages built, design system finalized, staging deploy |
| Phase 4 — Integrations | Sep 8 → Sep 21 | CMS APIs, Paystack, audio player, YouTube embed, webhooks |
| Phase 5 — Content + QA | Sep 22 → Oct 1 | Content uploaded, cross-browser QA, Lighthouse audit, SEO |
| Phase 6 — Launch | Oct 2 → Oct 9 | DNS flip, final tests, Google Search Console, GO LIVE |

### Phase 1 — Foundation Sprint (Now → Aug 3)

Patricia/AVO delivers all media assets (see checklist below)

Uncle Samson sets up Cloudflare DNS → staging/coming soon page

Uncle Samson bootstraps Strapi CMS and defines all schemas

Brother AY sets up Figma workspace with brand tokens

Micha: repo structure, Next.js initialized, .env files configured

### Phase 2 — UI Design (Aug 4 → Aug 17)

Brother AY: Figma hi-fi mockups for ALL pages (desktop + mobile)

Review session: Micha + Pastor approve layouts by Aug 14

Brother AY exports design tokens in Figma Dev Mode

Brother AY hands off Figma link to Micha

### Phase 3 — Core Frontend Build (Aug 18 → Sep 7)

Micha builds shared components: Navbar, Footer, all Card components

Micha builds all page layouts (Homepage, About, Resources, Articles, Programs, Giving, Events, Contact)

CSS system: design tokens, responsive grid, typography scale

Mid-checkpoint review (Aug 28): staging deploy for team review

### Phase 4 — Integrations (Sep 8 → Sep 21)

Samson: Paystack/Flutterwave API + webhook handlers

Micha: Connect frontend to Strapi APIs (sermons, events, articles, programs)

Micha: Audio player component, YouTube/Vimeo embed

Samson: Webhook → automated email confirmation on giving

### Phase 5 — Content Population + QA (Sep 22 → Oct 1)

Patricia/AVO uploads content to CMS: 10+ sermons, 5+ events, 5+ articles, all programs

Full team QA: Chrome, Safari, Firefox, iOS, Android

Viewport testing: 320px, 768px, 1024px, 1440px

Lighthouse performance audit: target ≥ 90 on all pages

SEO: meta titles, descriptions, OG images on all pages

### Phase 6 — Final Polish + Go Live (Oct 2 → Oct 9)

Samson flips Cloudflare DNS → production

End-to-end Paystack live transaction test

Google Search Console submission

Final Pastor sign-off

October 9: LAUNCH

## Media Asset Checklist (for Patricia / AVO)

[IMPORTANT] Send this list to the media team. Everything here is needed BEFORE Brother AY can start Figma hi-fi mockups.

### Brand Identity

Church Logo — SVG format (vector): full colour version + white/transparent version

Favicon — 32x32px PNG or ICO

Exact brand colour hex codes — Primary, secondary, accent (from official print materials)

Font names — Any specific fonts used in official church publications

Brand guidelines doc — If one exists (even a PDF)

### Photography

Pastor's portrait — Professional headshot, min 1200x1200px, transparent/white bg preferred

Leadership team portraits — Same spec for each leader/elder/deacon

Church interior photos — Wide shots of the hall, min 5 photos, min 2560x1440px

Church exterior / building photos — Min 3 photos

Congregation photos — People worshipping (with permission), candid + posed, min 10 photos

Event photos — Festival of Light, The Forge, Merismos, AAC, any major events. Min 5 per program.

Program-specific hero images — One strong image per program for card/banner photo

### Video / Audio

YouTube channel link (or Vimeo) — Where sermons are uploaded

Sermon archive — List of first 10 sermons (YouTube URLs + dates)

Any promo/intro video — Church welcome or vision video for homepage hero (optional but powerful)

### Content / Copy

Church address + location details

Service schedule — Days, times, service types

Phone numbers + WhatsApp number

Official social media handles — Instagram, YouTube, Facebook, Twitter/X, TikTok

Mission statement — 1-2 sentences, official version

Vision statement — Official version

Core values list — Named + brief description per value

Statement of beliefs / doctrinal positions — All points

Church bank account details — For giving page manual transfer option

Founding story — Brief write-up for About page

Program descriptions — For each: Festival of Light, The Forge, Merismos, AAC, others

## 5-Day Task List Per Team Member

Start Date: July 30, 2026  |  End of Sprint: August 3, 2026

### Patricia Osifo & AVO — Media / Design Consultancy

| Day | Task |
| --- | --- |
| Day 1 (Jul 30) | Review this plan. Confirm the full list of programs (names, descriptions) for the website. |
| Day 2 (Jul 31) | Export and send: Church logo (SVG, full colour + white variant), exact hex colour codes, official font names. |
| Day 3 (Aug 1) | Gather and send: Pastor portrait + all leadership portraits (high-res). |
| Day 4 (Aug 2) | Gather and send: Church interior/exterior photos + congregation photos (min 10 total). |
| Day 5 (Aug 3) | Send: Event photos per program, program descriptions (name + tagline + 2-3 para each), service schedule, phone numbers, social handles, bank details, mission + vision statements. |

### Brother AY — UI Designer

| Day | Task |
| --- | --- |
| Day 1 (Jul 30) | Review this plan. Confirm you understand all 8 pages and their sub-sections. |
| Day 2 (Jul 31) | Set up Figma project. Create colour palette, typography scale, button styles, spacing tokens as soon as brand assets arrive from AVO. |
| Day 3 (Aug 1) | Begin Homepage wireframe (low-fidelity) — define hero, section order, card grids. |
| Day 4 (Aug 2) | Begin About page wireframe — 4-section structure (Who We Are / What to Expect / Beliefs / Leadership). |
| Day 5 (Aug 3) | Begin Giving page wireframe. Share Figma link with Micha for early feedback. Note any blockers. |

### Uncle Samson — Backend / Dev

| Day | Task |
| --- | --- |
| Day 1 (Jul 30) | Review this plan. Confirm Strapi as the CMS. Confirm Vercel for hosting. Post decisions to group. |
| Day 2 (Jul 31) | Cloudflare DNS: point thepublishershouse.org to a temporary 'Coming Soon' staging page. |
| Day 3 (Aug 1) | Create Strapi project. Define Sermon schema (Title, Speaker, Date, YouTubeURL, AudioURL, StudyGuideURL, Series, Tags). |
| Day 4 (Aug 2) | Define Event schema + Article schema. Create Vercel project, link to GitHub repo. |
| Day 5 (Aug 3) | Define Program schema + Leadership schema. Share Strapi API URL + token with Micha. |

### Micha — Vibecoder / Frontend / Coordinator

| Day | Task |
| --- | --- |
| Day 1 (Jul 30) | Review and approve this plan. Share with team. Set group check-in cadence. |
| Day 2 (Jul 31) | Next.js 14 project initialized. Repo structure set up. Pushed to GitHub. |
| Day 3 (Aug 1) | Global CSS design system built (tokens, typography, spacing, animations). Navbar shell built. |
| Day 4 (Aug 2) | Footer built. All page route files created (/, /about, /resources, /programs, /articles, /events, /giving, /contact). |
| Day 5 (Aug 3) | Strapi API layer built (/lib/strapi.ts). .env.example created. Dev server running at localhost:3000. |

## Confirmed Technical Decisions

| Decision | Choice | Status |
| --- | --- | --- |
| Frontend Framework | Next.js 14 (App Router) | Confirmed |
| CMS | Strapi | Confirmed (Samson) |
| Payment Gateway | Paystack / Flutterwave | Confirmed (per PRD) |
| Domain / CDN | Cloudflare (domain already live) | Confirmed |
| App Hosting | Vercel (zero-config Next.js) | Pending Samson setup |
| Giving Currency | NGN (Naira) | Pending multi-currency confirmation |

## Still Pending

[NOTE] Program full names: Patricia/AVO to confirm full official names of ALL programs — especially 'AAC' and any beyond the 4 mentioned.

[NOTE] Giving amounts: Confirm preset giving amounts in NGN for the Giving page form.

[NOTE] Vercel deploy: Samson to create Vercel project and link to GitHub repo for auto-deploy on push to main.

## Update Policy

This document is a living plan. As new pages, features, or programs are added:

Micha updates this doc and notifies the team

Brother AY adds the new page to Figma

Uncle Samson adds the new schema to CMS if needed

Patricia/AVO provides assets for new content